## Sheet1
2001 Title 24 Publication Agreements Status Report
[7 empty] | Report Date: | 2001-08-22 16:34
Part/Description | Publish'r | PA Draft Sent | Response Received | Second Draft Sent | Response Received | PA Sent For Signature | Signed PA Received | PA Executed & Sent
Part 2 | ICBO
Building Code |  | May 18, 2001 |  | May 22, 2001 | July 28, 2001 | Agust 3, 2001 | August 17, 2001 | August 22, 2001
Part 3 | NFPA |  |  | Responded |  | August 2, 2001, Then
Electrical Code |  | May 23, 2001 | July 6, 2001 | July 12, 2001 | July 20, 2001 | Rev. Pages Aug. 14, 01
(Sent To Stan For Sec.
Part 4 | IAPMO | May 22, 01 (CMC) |  |  |  | Adams Review 8/13/01)
Mechanical Code |  | June 8, 2001 (CMC) | July 6, 2001 | July 17, 2001 |  | August 13, 2001
Again August 21, 2001
Part 5 | IAPMO | May 22, 2001 |  |  |  | Adams Review 8/13/01)
Plumbing Code |  | June 8, 2001 | July 6, 2001 | July 17, 01 | August 9, 2001 | August 13, 2001
Again August 21, 2001
('98 ICBO PA As Req.
Part 9 | WFCA | May 31, 2001 By FAX) | Sent e-mail 8/15/01 | e-m'd PA to JM 8/20/01
Fire Code |  | June 1, 2001 | 8/17/01 - McMullen FAX
Part 10 | ICBO
Code 4 Bldg Conservaton |  | June 4, 2001 | (See Part 2) |  |  | August 3, 2001 | Agust 17, 2001 | August 22, 2001
Parts 1, 6, 7, 8 & 12 | ICBO
Administrative Code
Energy Code
Elevator Safety Const
Historical Building Code
Referenced Standards |  | June 4, 2001 | (See Part 2) |  |  | August 1, 2001 | August 17, 2001 | August 22, 2001
H:\SLP\BSC\2001 CBSC Publication\PA Schedule