CURRENT  PUBLICATION  SCHEDULE

2001  TITLE  24,  PARTS  1,  2,  3,  4,  5,  6,  7,  8,  9,  10  AND  12

This Publication Schedule Is Dated January 17, 2002 – 11: 00 A.M. PST

Please be advised that this schedule is subject to change without notice.

1)	Between Today and March 20, 2001

- Publishers submit drafts to BSC staff for review and corrections

- Allow two weeks between BSC receipt and return - Agencies also review

- BSC staff must see “corrected” drafts showing that corrections have been made

- BSC to issue final approval of completely corrected draft

(sans publication and effective dates)

2)	March 20, 2001 –  A  CRITICAL  MILESTONE  DATE:

- All Parts final drafts approved, ready to print except for

- Publication Date insertion in Historical Appendix

- Effective Date insertion on Title Page

3)	March 20, 2002 – California Building Standards Commission Meeting:

  - Complete adoption of all parts of 2001 Title 24

  - Establish Effective Date of 2001 Title 24

4)	March 20-21, 2002:

- Notify publishers of adoption completion

- Notify publishers of Effective Date

5)	May 3, 2002 –  THIS  IS  A  DROP  DEAD  DEADLINE !

- All 2001 Title 24 volumes on the shelf and available to general public

- Not a promise or fictitious date - on the shelf for immediate delivery to customers!

6)	November 1, 2002 – Effective Date of the 2001 Title 24, Parts 1, 2, 3, 4, 5, 6, 7, 8, 9 ,10 & 12

H:\SLP\BSC\2001 CBSC Publication\Publication Schedule