## Sheet1
|  |  |  | FEBRUARY |  |  |  | MARCH |  |  | APRIL |  |  | MAY
|  |  | SENT TO | 1ST PROOF | RET'D | FROM | AGENCY | 2ND PROOF | AGENCY | RET'D | 3RD PROOF | AGENCY | RET'D | FINAL REVIEW
STAFF | PART | AGENCIES | PUBLISHER | RCVD | TO P'R | P'R | REVIEWS | RCVD | REVIEWS | TO P'R | RCVD | REVIEWS | TO PR | DEADLINE
ICC
MIKE | 1 |  | 2013-01-18 | [10 empty] | 2013-05-15
BSC 02/12
DSA-SS 01/12
DSA-AC 02/12
OSHPD EF 01/11
OSHPD 02/12
OSHPD 03/12
MIKE/MIA | 2 |  | 2013-02-15 | [10 empty] | 2013-05-15
BSC 03/12
CDPH 01/12
CSA (BSCC) 01/12
DSA-AC EF 01/12
DSA-AC 01/12
DSA-SS 02/12
HCD 06/12
HCD 08/12 (11A)
OSHPD EF 01/13
OSHPD 03/12 SS
OSHPD 04/12
SFM 02/12
SLC 01/12
RUSS | 2.5 |  | 2013-02-11 | [10 empty] | 2013-05-15
SFM 04/12
HCD 03/12
ENRIQUE | 6 |  | 2013-02-11 | [10 empty] | 2013-05-15
CEC 02/12
|  |  |  | FEBRUARY |  |  |  | MARCH |  |  | APRIL |  |  | MAY
|  |  | SENT TO | 1ST PROOF | RET'D | FROM | AGENCY | 2ND PROOF | AGENCY | RET'D | 3RD PROOF | AGENCY | RET'D | FINAL REVIEW
STAFF | PART | AGENCIES | PUBLISHER | RCVD | TO P'R | P'R | REVIEWS | RCVD | REVIEWS | TO P'R | RCVD | REVIEWS | TO PR | DEADLINE
MIKE | 8 |  | 2013-12-10 | 2013-01-07 | 2013-02-12 | [8 empty] | 2013-05-15
SHBSB 01/12
RUSS | 9 |  | 2013-02-11 | [10 empty] | 2013-05-15
SFM 03/12
MIKE | 10 |  | 2013-12-10 | 2013-01-07 | [9 empty] | 2013-05-15
|  | BSC 06/12 |  |  | 2013-02-12
|  | HCD 07/12 |  |  | 2013-02-12 |  | 2013-02-11
ENRIQUE | 11 |  | 2013-02-11 | [10 empty] | 2013-05-15
BSC 07/12
CEC 01/12
DSA-SS 06/12
HCD 04/12
MIKE | 12 |  | 2013-12-10 | 2013-01-07 | 2013-02-12 | [8 empty] | 2013-05-15
SFM 07/12
BNi/NFPA
MIKE | 3 |  | 2013-12-10 | 2013-01-16 | 2013-02-05 | 2013-02-13 | [7 empty] | 2013-05-15
BSC 01/12
DSA-SS 03/12
HCD 01/12
OSHPD 01/12
SFM 01/12
|  |  |  | FEBRUARY |  |  |  | MARCH |  |  | APRIL |  |  | MAY
|  |  | SENT TO | 1ST PROOF | RET'D | FROM | AGENCY | 2ND PROOF | AGENCY | RET'D | 3RD PROOF | AGENCY | RET'D | FINAL REVIEW
STAFF | PART | AGENCIES | PUBLISHER | RCVD | TO P'R | P'R | REVIEWS | RCVD | REVIEWS | TO P'R | RCVD | REVIEWS | TO PR | DEADLINE
IAPMO
MIA | 4 |  | 2013-01-25 | [10 empty] | 2013-05-15
BSC 04/12
DSA-SS 04/12
HCD 02/12
OSHPD 05/12
SFM 05/12
√OSHPD 3SE
MIA | 5 |  | 2013-02-06 | [10 empty] | 2013-05-15
BSC 05/12
DSA-SS 05/12
DWR 01/12
HCD 05/12
OSHPD 06/12
SFM 06/12
√OSHPD 3SE
*blue
indicates
files yet
to be
sent
AGENCY
|  | BSC | CSA/BSCC | CDPH | CEC | DSA-SS | DSA-AC | HCD | OSHPD | SFM | SLC | SHBSB | DWR
|  | green | pink | turquoise | purple | yellow | yellow | orange | blue | red | purple | yellow | turquoise
| PART | 1 |  |  |  | 1 | 1 |  | 1
|  | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2
|  | 2.5 | [5 empty] | 2.5 |  | 2.5
|  | 3 |  |  |  | 3 |  | 3 | 3 | 3
|  | 4 |  |  |  | 4 |  | 4 | 4 | 4
|  | 5 |  |  |  | 5 |  | 5 | 5 | 5 |  |  | 5
6
8
9
|  | 10 | [5 empty] | 10
|  | 11 |  |  | 11 | 11 |  | 11
12
|  | BSC | CSA/BSCC | CDPH | CEC | DSA-SS | DSA-AC | HCD | OSHPD | SFM | SLC | SHBSB | DWR
| Contacts | Mike | Allison | Eric | Ron | Chip | Derek | Shawn | Patt | Kevin | Maria | Chip | Saare
|  |  | Ganter | Trevena | Yazney | Smith | Shaw | Huff | Friel | Reinertson |  | Smith | Edmonds
|  |  | 323-8617 | 449-5695 | 651-2915 | 322-4699 | 324-7178 | 327-2816 | 440.8417 |  | 574-1800 | 322-4699 | 651-9676
[5 empty] | Pippin |  |  | Kyle | Glenn |  | John |  | Julie
[5 empty] | Brehler |  |  | Krause | Gall |  | F
324-7991
Doug
Hensel